## Activity-bar-chart
Trình lập kế hoạch Dự án
Chọn một khoảng thời gian để tô sáng ở bên phải. Chú giải mô tả lập biểu đồ theo sau. |  |  |  | Tô sáng Khoảng thời gian: |  | 1 |  |  | Tổng thời gian | [8 empty] | % Hoàn tất
HOẠT ĐỘNG | NGƯỜI THỰC HIỆN | GHI CHÚ | LẬP KẾ HOẠCH BẮT ĐẦU | LẬP KẾ HOẠCH THỜI LƯỢNG | PHẦN TRĂM HOÀN THÀNH
[6 empty] | 11-19/10 | 20-27/10 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25 | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18 | 2021-12-19 | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25 | 2021-12-26
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
Xây dựng Team Workflow | Nhóm |  | 1 | 1 | 100%
Training Git & Trello | Thanh |  | 2 | 1 | 100%
Lên kế hoạch dự án | Nhóm |  | 3 | 2 | 100%
Khảo sát thị trường | Nhóm |  | 5 | 1 | 100%
Phân tích chức năng |  |  | 7 | 5 | 100%
Phân tích chức năng hệ thống | Thanh, Đức, Thắng, Quân. | Với vai trò là khách hàng | 7 | 1 | 100%
Phân tích chức năng người dùng | Phú, Duyên, Duy, Dũng | Với vai trò là khách hàng | 7 | 1 | 100%
Phỏng vấn khách hàng |  | Với vai trò là lập trình viên | 9 | 1 | 100%
PV nhân viên thủ tục liên hàng không | Quân | Chức năng quản lý vé | 9 | 1 | 100%
PV nhân viên kiểm toán, kế toán | Duyên | Chức năng thanh toán, thống kê | 9 | 1 | 100%
PV nhân viên marketing | Duy | Chức năng cho người dùng | 9 | 1 | 100%
PV bộ phận quản lý hàng không sân bay | Đức | Chức năng quản lý sân bay | 9 | 1 | 100%
PV bộ phận giám sát chất lượng dịch vụ và vận tải hàng không | Thắng | Chức năng quản lý chuyến bay | 9 | 1 | 100%
PV bộ phận nhân sự | Dũng | Chức năng quản lý nhân viên | 9 | 1 | 100%
PV nhân viên kinh doanh | Phú | Chức năng quản lý thông tin hãng hàng không | 9 | 1 | 100%
Tổng hợp user story | Thanh |  | 11 | 1 | 100%
Xây dựng product backlog | Thanh |  | 12 | 2 | 100%
Thiết kế cơ sở dữ liệu | Quân, Thắng, Duy, Dũng, Phú, Đức, Duyên |  | 11 | 3 | 100%
Quản lý vé máy bay | Duy | Story Points: 10 | 13 | 7 | 60%
FE: C.R.U.D Ticket |  |  | 13 | 7 | 80%
FE: search |  |  | 13 | 7 | 80%
BE: C.R.U.D Ticket |  |  | 13 | 7 | 80%
BE: search |  |  | 13 | 7 | 80%
Test |  |  | 13 | 7 | 80%
Quản lý chuyến bay | Dũng | Story Point:s 14 | 13 | 7 | 80%
FE: C.R.U.D Flight |  |  | 13 | 7 | 80%
FE: Search |  |  | 13 | 7 | 80%
FE: getFlights |  |  | 13 | 7 | 80%
FE: getFlight |  |  | 13 | 7 | 80%
BE: C.R.U.D Flight |  |  | 13 | 7 | 80%
BE: search |  |  | 13 | 7 | 80%
BE: getFlights |  |  | 13 | 7 | 80%
BE: getFlight |  |  | 13 | 7 | 80%
Test |  |  | 13 | 7 | 80%
Quản lý hãng hàng không | Duyên | Story Points: 14 | 13 | 7 | 80%
FE: C.R.U.D Airline |  |  | 13 | 7 | 80%
FE: Search |  |  | 13 | 7 | 80%
FE: getAirlines |  |  | 13 | 7 | 80%
FE: getAirline |  |  | 13 | 7 | 80%
BE: C.R.U.D Airline |  |  | 13 | 7 | 80%
BE: search |  |  | 13 | 7 | 80%
BE: getAirlines |  |  | 13 | 7 | 80%
BE: getAirline |  |  | 13 | 7 | 80%
Test |  |  | 13 | 7 | 80%
Quản lý chương trình khuyến mãi | Đức | Story Points: 14 | 20 | 7 | 80%
FE: C.R.U.D Promotion |  |  | 20 | 7 | 80%
FE: Search |  |  | 20 | 7 | 80%
FE: getPromotions |  |  | 20 | 7 | 80%
FE: getPromotion |  |  | 20 | 7 | 80%
BE: C.R.U.D Promotion |  |  | 20 | 7 | 80%
BE: search |  |  | 20 | 7 | 80%
BE: getPromotions |  |  | 20 | 7 | 80%
BE: getPromotion |  |  | 20 | 7 | 80%
Test |  |  | 20 | 7 | 80%
Quản lý sân bay | Phú | Story Points: 16 | 20 | 7 | 80%
FE: C.R.U.D Airport |  |  | 20 | 7 | 80%
FE: Search |  |  | 20 | 7 | 80%
FE: getAirports |  |  | 20 | 7 | 80%
FE: getAirport |  |  | 20 | 7 | 80%
BE: C.R.U.D Airport |  |  | 20 | 7 | 80%
BE: search |  |  | 20 | 7 | 80%
BE: getAirports |  |  | 20 | 7 | 80%
BE: getAirport |  |  | 20 | 7 | 80%
Test |  |  | 20 | 7 | 80%
Quản lý máy bay | Quân | Story Points: 14 | 27 | 7 | 80%
FE: C.R.U.D Plane |  |  | 20 | 7 | 80%
FE: Search |  |  | 27 | 7 | 80%
FE: getPlanes |  |  | 27 | 7 | 80%
FE: getPlane |  |  | 27 | 7 | 80%
BE: C.R.U.D Plane |  |  | 20 | 7 | 80%
BE: search |  |  | 27 | 7 | 80%
BE: getPlanes |  |  | 27 | 7 | 80%
BE: getPlane |  |  | 27 | 7 | 80%
Test |  |  | 27 | 7 | 80%
Quản lý đặt vé | Thanh | Story Points: 21 | 27 | 7 | 80%
FE: bookTickets |  |  | 27 | 7 | 80%
FE: getBookedTickets |  |  | 27 | 7 | 80%
FE: getFlights |  |  | 27 | 7 | 80%
FE: getAirlines |  |  | 27 | 7 | 80%
FE: getTimes |  |  | 27 | 7 | 80%
FE: changeTicket |  |  | 27 | 7 | 80%
FE: cancelTicket |  |  | 27 | 7 | 80%
FE: searchBy |  |  | 27 | 7 | 80%
FE: getPromotions |  |  | 27 | 7 | 80%
FE: getPayMethods |  |  | 27 | 7 | 80%
FE: autoBuyTickets |  |  | 27 | 7 | 80%
FE: accumulatePoints |  |  | 34 | 7 | 80%
FE: huntingSaleTickets |  |  | 27 | 7 | 80%
FE: payment |  |  | 27 | 7 | 80%
BE: bookTickets |  |  | 27 | 7 | 80%
BE: getBookedTickets |  |  | 27 | 7 | 80%
BE: getTimes |  |  | 27 | 7 | 80%
BE: changeTicket |  |  | 27 | 7 | 80%
BE: cancelTicket |  |  | 27 | 7 | 80%
BE: searchBy |  |  | 27 | 7 | 80%
BE: getPayMethods |  |  | 27 | 7 | 80%
BE: autoBuyTickets |  |  | 27 | 7 | 80%
BE: accumulatePoints |  |  | 34 | 7 | 80%
BE: getPoints |  |  | 34 | 7 | 80%
BE: huntingSaleTickets |  |  | 27 | 7 | 80%
BE: payment |  |  | 27 | 7 | 80%
Test |  |  | 27 | 7 | 80%
Quản lý tài khoản | Thắng | Story Points: 14 | 34 | 7 | 80%
FE: C.R.D Account |  |  | 34 | 7 | 80%
FE: Search |  |  | 34 | 7 | 80%
FE: getAccounts |  |  | 34 | 7 | 80%
FE: lockAccount |  |  | 34 | 7 | 80%
FE: restorePassword |  |  | 34 | 7 | 80%
BE: C.R.D Account |  |  | 34 | 7 | 80%
BE: search |  |  | 34 | 7 | 80%
BE: getAccounts |  |  | 34 | 7 | 80%
BE: lockAccount |  |  | 34 | 7 | 80%
BE: restorePassword |  |  | 34 | 7 | 80%
Test |  |  | 34 | 7 | 80%
Quản lý khách hàng | Duy | Story Points: 18 | 34 | 7 | 80%
FE: C.R.U.D Customer |  |  | 34 | 7 | 80%
FE: Search |  |  | 34 | 7 | 80%
FE: getCustomers |  |  | 34 | 7 | 80%
FE: getCustomer |  |  | 34 | 7 | 80%
FE: EXIM Customer Excel |  |  | 34 | 7 | 80%
BE: C.R.U.D Customer |  |  | 34 | 7 | 80%
BE: search |  |  | 34 | 7 | 80%
BE: getCustomers |  |  | 34 | 7 | 80%
BE: getCustomer |  |  | 34 | 7 | 80%
BE: EXIM Customer Excel |  |  | 34 | 7 | 80%
Test |  |  | 34 | 7 | 80%
Quản lý hạng khách hàng | Dũng | Story Points: 14 | 34 | 7 | 80%
FE: C.R.U.D Rank |  |  | 34 | 7 | 80%
FE: Search |  |  | 34 | 7 | 80%
FE: getRanks |  |  | 34 | 7 | 80%
FE: getRank |  |  | 34 | 7 | 80%
BE: C.R.U.D Rank |  |  | 34 | 7 | 80%
BE: search |  |  | 34 | 7 | 80%
BE: getRanks |  |  | 34 | 7 | 80%
BE: getRank |  |  | 34 | 7 | 80%
Test |  |  | 34 | 7 | 80%
Quản lý nhân viên | Duyên | Story Points: 18 | 41 | 10 | 80%
FE: C.R.U.D Staff |  |  | 41 | 10 | 80%
FE: Search |  |  | 41 | 10 | 80%
FE: getStaffs |  |  | 41 | 10 | 80%
FE: getStaff |  |  | 41 | 10 | 80%
FE: EXIM Staff Excel |  |  | 41 | 10 | 80%
BE: C.R.U.D Staff |  |  | 41 | 10 | 80%
BE: search |  |  | 41 | 10 | 80%
BE: getStaffs |  |  | 41 | 10 | 80%
BE: getStaff |  |  | 41 | 10 | 80%
BE: EXIM Staff Excel |  |  | 41 | 10 | 80%
Test |  |  | 41 | 10 | 80%
Quản lý chức vụ | Đức | Story Points: 14 | 41 | 10 | 80%
FE: C.R.U.D Position |  |  | 41 | 10 | 80%
FE: Search |  |  | 41 | 10 | 80%
FE: getPositions |  |  | 41 | 10 | 80%
FE: getPosition |  |  | 41 | 10 | 80%
BE: C.R.U.D Position |  |  | 41 | 10 | 80%
BE: search |  |  | 41 | 10 | 80%
BE: getPositions |  |  | 41 | 10 | 80%
BE: getPosition |  |  | 41 | 10 | 80%
Test |  |  | 41 | 10 | 80%
Quản lý đăng nhập đăng ký | Phú | Story Points: 10 | 41 | 10 | 80%
FE: resigter |  |  | 41 | 10 | 80%
FE: login/logout |  |  | 41 | 10 | 80%
BE: resigter |  |  | 41 | 10 | 80%
BE: login/logout |  |  | 41 | 10 | 80%
Test |  |  | 41 | 10 | 80%
Thống kê doanh thu | Quân | Story Points: 18 | 41 | 10 | 80%
FE: statisticsByDay |  |  | 41 | 10 | 80%
FE: statisticsByMonth |  |  | 41 | 10 | 80%
FE: statisticsByQuarterly |  |  | 41 | 10 | 80%
FE: statisticsByYear |  |  | 41 | 10 | 80%
BE: statisticsByDay |  |  | 41 | 10 | 83%
BE: statisticsByMonth |  |  | 41 | 10 | 80%
BE: statisticsByQuarterly |  |  | 41 | 10 | 70%
BE: statisticsByYear |  |  | 41 | 10 | 80%
Test |  |  | 41 | 10 | 80%
Quản lý ví thanh toán | Thanh | Story Points: 18 | 41 | 10 | 80%
FE: bankConnection |  |  | 41 | 10 | 80%
FE: topUp |  |  | 41 | 10 | 80%
FE: withdraw |  |  | 41 | 10 | 80%
FE: payment |  |  | 41 | 10 | 80%
FE: paymentHistory |  |  | 41 | 10 | 80%
BE: bankConnection |  |  | 41 | 10 | 40%
BE: topUp |  |  | 41 | 10 | 80%
BE: withdraw |  |  | 41 | 10 | 65%
BE: payment |  |  | 41 | 10 | 80%
BE: paymentHistory |  |  | 41 | 10 | 60%
Test |  |  | 41 | 10 | 80%